## Features
Sr. No | Artifact | Feature/Requirement | Page Ref | Our Recommendation for Demo | Estimates In Hours | Solution Approach( Estimation Details)
1 | Initial screen | button for color setting leading to color setting screen | 1,2 | Phase1 | 12 | Initial project Workspae setup Working on this color setting
1 | Initial screen | Screen for color setting | 1,2 | Phase1 | 6 | to provide color settings for the screen
2 | Initial screen | History inquiry for Unit history, aircraft position history and System history - launch button | 1,2 | Phase1 | 16 | Dummy data set up and services creation for getting the dummy data
3 | Initial screen | Display of component removal codes. Each button in "reference table" will display corrosponding list of codes in corrosponding screen | 1,2 | Phase1 | 8 | data retrieval via appropriate micro service calling
4 | Unit based filter editor screen | set a filter name - textbox | 4 | Phase1 | 8 | Setting the filter name
5 | Unit based filter editor screen | Selection of date range | 5 | Phase1 | 8 | Creation of date range ui components
6 | Unit based filter editor screen | Grouping by manufacturer’s part numbers, installed units,non active units, problem units, overhoul units | 5 | Phase1 | 8 | Logic to group part numbers based on the given criterias
7 | Unit based filter editor screen | Sorting by serial number, removal numbers, last installation date, last removal date | 5 | Phase1 | 7 | Sorting and pagination logic to be implemented
8 | Unit based filter editor screen | Clear the list of serial numbers | 4,5 | Phase1 | 4 | UI change to clear the list of Serial Numbers
9 | Unit based filter editor screen | clear the list of mfg part numbers | 4,5 | Phase1 | 8 | UI change to clear the list of MFG part numbers
10 | Unit based filter editor screen | Save filter,Save filter as, Use default filter, Use saved settings, cancel, ok | 4,5 | Phase1 | 8 | Setting the various conditional based filtering in the settings widget
11 | Unit based filter editor screen | Load saved filter button should show all the previously saved filters | 4,5 | Phase1 | 7 | Storing the previously saved filters in database and retrieving the same when Load saved filter button is clicked
12 | Unit based filter editor screen | Select multiple serial numbers and mfg. part numbers based on which the number will be shown in "Selected" at the bottom | 4,5 | Phase1 | 8 | Setting up the criteria on which the number has to be shown
13 | Component removal screen - Toolbar | Print and/or save - dropdown | 7 | Phase1 | 12 | Adding Print Related View and saving the generated data.
14 | Component removal screen - Toolbar | View - removal or exclusion of duration parameters for eg. Remove monthly column display - dropdown | 7 | Phase1 | 5 | UI change Required for Removal of Monthly column display
15 | Component removal screen - Toolbar | Statistics - Display data as an MTBUR graph - dropdown | 7 | Phase1 | 12 | Creation of Graphs using Graph js library
16 | Component removal screen | Display basic information of the selected component such as CPN, description, ATA, unit count, displayed unit count, date range, first install date and query extract date (uneditable) | 10 | Phase1 | 8 | Retrieving the data for selected components
17 | Component removal screen | "Unit count" - auto populate - includes all units with history in our database, including units purged or sold that we owned previously | 10 | Phase1 | 3 | Getting the unit Count populated
18 | Component removal screen | Displayed count - auto populate - depends on what selections you made such as serial numbers omitted, and units that are “inactive” if you chose not to display them. | 10 | Phase1 | 8 | Auto Populate based on serial numbers.. UI change would be required
19 | Component removal screen | Scrollable list of selected serial numbers in black font ,serial numbers with units not in active inventory in red font , serial numbers withunits that have problematic removal data in purple font | 10 | Phase1 | 3 | UI as well as Service changes Require
20 | Component removal screen | bar graph depicting unit performance overlaying a monthly calendar graph. the dark blue bars indicate unit time in revenue service. Gray bars would indicate units installed on inactive aircraft. Red bars would be indicative of other service time, such as units loaned to other operators. | 10 | Phase1 | 8 | UI Changes Required Testing
21 | Component removal screen | selectable color-coded “tick” marks corresponding to each unit removal : Hide / display based on user's choice to indicate indicate whether the unit had an unscheduled removal, a scheduled removal, or other removal type such as aircraft swap or rob | 10 | Phase1 | 12 | UI Changes Required Testing
22 | Component removal screen | pink box at the far right end of the installation bar indicates that the unit is currently in service for every serial number - Hide / display based on the checkbox | 10 | Phase1 | 8 | UI Changes Required
23 | Component removal screen | display supporting data with "mousing over" feature | 10 | Phase1 | 12 | UI Changes Required
24 | Screen from "Tools" dropdown in Component removal screen | Tools - with dropdown options removal count by month and year , removals by date for a selected month | 11 | Phase 2 | 8 | UI Changes Required
25 | Screen from "Tools" dropdown in Component removal screen | Screen showing graph with duration in months on X-axis and no. of removals(scheduled,unscheduled,other) on Y-axis. | 12 | Phase 2 | 8 | UI Changes Required
26 | Screen from "Tools" dropdown in Component removal screen | Screen showing graph with duration in days of a month on X-axis and no. of removals(scheduled,unscheduled,other) on Y-axis. | 12 | Phase 2 | 7 | UI Changes Required
27 | Aircraft position based filter editior | set a filter name - textbox | 14 | Phase 2 | 6 | UI Changes Required
28 | Aircraft position based filter editior | Selection of date range | 14 | Phase 2 | 8 | UI as well as Service changes Require
29 | Aircraft position based filter editior | Grouping of tail numbers by Incactive aircraft, problem history aircraft, fleet, position and no grouping | 14 | Phase 2 | 12 | Logic to group part numbers based on the given criterias
30 | Aircraft position based filter editior | "Sort by" with a dropdown menu | 14 | Phase 2 | 12 | Sorting and pagination logic to be implemented
31 | Aircraft position based filter editior | Selection of tail numbers, positions and fleet codes generated based on the grouping criteria | 14 | Phase 2 | 16 | UI as well as Service changes Require
32 | Aircraft position based filter editior | Uneditable fields to show selected tail numbers, positions and fleet codes | 14 | Phase 2 | 8 | UI as well as Service changes Require
33 | Aircraft position based filter editior | buttons to "clear all" selections | 14 | Phase 2 | 8 | UI as well as Service changes Require
34 | Aircraft position based filter editior | Buttons to use saved setting, load a list of saved settings, save filter and save filter as, cancel and ok | 14 | Phase 2 | 12 | UI as well as Service changes Require
35 | Component history by aircraft / fleet screen - toolbar | Print and/or save - dropdown | 17 | Phase 3 | 8 | UI as well as Service changes Require
36 | Component history by aircraft / fleet screen - toolbar | View - removal or exclusion of duration parameters for eg. Remove monthly column display - dropdown | 17 | Phase 3 | 8 | UI as well as Service changes Require
37 | Component history by aircraft / fleet screen - toolbar | Statistics - Display data as an MTBUR graph - dropdown | 17 | Phase 3 | 12 | UI as well as Service changes Require
38 | Component history by aircraft / fleet screen | Display basic information of the selected aircraft tail number such as part information, first installation, extract date, date range, aircraft position count and displayed count (uneditable) | 17 | Phase 3 | 6 | UI Changes Required
39 | Component history by aircraft / fleet screen | scrollable list of selected fleet or aircraft tail numbers along the left side of the display | 17 | Phase 3 | 8 | UI Changes Required
40 | Component history by aircraft / fleet screen | color-coded horizontal bar graph to the right of the tail numbers, overlaid on a reference calendar graph with different color segments indicating “up” time (available for revenue service) as well as “down” time | 17 | Phase 3 | 8 | UI Changes Required
41 | Component history by aircraft / fleet screen | "clicking on" / "mousing over" feature to open a quick window over the segment of the bar showing details such as station, flight number, delay/cancellation data, ATA, out of service time, ETIC and the PDIS, MDIS, MTSI or SMPI that has caused the aircraft to go into the “down” status | 18 | Phase 3 | 8 | UI Changes Required
42 | Component history by aircraft / fleet screen | Weekly view - clicking or mousing over the display bar segments would display flight time, flight number, departure and arrival stations, and flight duration. | 18 | Phase 3 | 9 | UI Changes Required
43 | Component history by aircraft / fleet screen | checkbox to display / hide selected maintenance activity and significant events by ATA with the help of color coded letter to indicate a PDIS, MDIS, MTSI, SMPI, MEL or EA.(display a minimum of four ATA’s per aircraft with six being the optimal number) | 18 | Phase 3 | 12 | UI Changes Required
44 | Component history by aircraft / fleet screen | “clicking on” or “mousing over” a given tick mark or letter box indication, a window would open detailing the associated log entry | 18 | Phase 3 | 8 | UI Changes Required
Note on C18: Parag Amrutsagar: How will the information be displayed in case of multiple component selection
Note on C22: Parag Amrutsagar: Will the bar graph be shown per unit / serial number.
Note on C45: Parag Amrutsagar: These acronyms are some kind of aircraft standars.

## Queries
Sr. No | Feature/Requirement | Page Ref | Our Recommendation for Demo | Estimates In Hours | Solution Approach( Estimation Details) | Query
1 |  | 1 |  |  |  | Is component performance related to the productivity / maaintainence of the componets? What is the scope if "component"?
2 |  | 1 |  |  |  | Does "component history" mean when was the componet installed, removed etc from the component? What details of the component and aircraft?
3 |  | 1 |  |  |  | what exactly "System" is referred to as here?
4 |  | 2 |  |  |  | what exacty is a "Unit"? Is it individual sub part of a component ? Is unit same as that of component or is it the subset of component like, one component may have many units?
5 |  | 2 |  |  |  | UI - what is "Aircraft position"?
6 |  | 2 |  |  |  | What do "codes" specified in reference table signify?
7 |  | 2 |  |  |  | Will the buttons in the diagram on pg. 1 open individual screens?
8 |  | 4 |  |  |  | What is the trigger for UI on page 4?
9 |  | 4 |  |  |  | Does "Active aircraft" mean aircraft in revenue service?
10 |  | 4 |  |  |  | Need a brief description about the types of units.
11 |  | 7 |  |  |  | Is "extract date/ report date" the date at which the user is presented the data when he/she asked for?
12 |  | 7 |  |  |  | What does MTBUR signify and how is it considered in diagram on page 7?
13 |  | 8 |  |  |  | What is "Aircraft tail" and "aircraft tail number"?
14 |  | 14 |  |  |  | what do we mean by "ability to look at component removals in relation to tail number and positions?
15 | [5 empty] | What are the triggers for each UI in the document? What is the end to end flow of user /system interaction?